## Summary Dashboard
KAVIN TRAVELS — Quality Assurance & Security Audit Dashboard
Application Audit, Vulnerability Remediation, Test Execution & Verification Summary ¦ October 2026
Bug Metrics | Count | Testing Performance | Count | Audit Verdict
Total Bugs Found |  | Total Manual Test Cases |  | APPLICATION STATUS
Critical Bugs |  | Manual Tests Passed |  | PASS / STABILIZED
High-Severity Bugs |  | Manual Tests Failed
Medium-Severity Bugs |  | Manual Tests Not Executed |  | OVERALL FIX RATE
Low-Severity Bugs |  | Total Automated Tests |  | 100.0%
Bugs Fixed & Verified |  | Automated Tests Passed
Open Bugs |  | Automated Tests Failed |  | AUTOMATED PASS RATE
Partially Fixed Bugs |  | Automated Tests Skipped |  | 100.0% (25/25)
Retest Required |  | Security Audit Findings
Blocked Issues |  | Security Remediations Verified
Severity | Count | Status | Count | Testing Category | Passed | Failed
Critical |  | Fixed |  | Manual Tests
High |  | Open |  | Automated Tests
Medium |  | Blocked
Low

## Bug Tracker
Bug ID | Date Found | Module | Bug Title | Bug Description | Reproduction Steps | Expected Result | Actual Result | Severity | Priority | Root Cause | Fix Applied | Files Changed | Test Case ID | Test Evidence | Fix Status | Retest Result | Date Fixed | Verified By | Remarks
BUG-001 | 2026-10-03 | Backend Config | Plaintext root database password in application.properties | Root MySQL password (nivak@0328) was committed in application.properties source code. | Open backend/src/main/resources/application.properties and inspect line 15. | Database passwords must be externalized via environment variables. | Root password was committed directly in plaintext to version control. | Critical | P0 | Hardcoded fallback in properties file. | Replaced password default with ${DB_PASSWORD} without sensitive fallback; created sanitized application-example.properties. | application.properties, application-example.properties | TC-MAN-001 | Properties inspected, verified parameterized | Fixed | Pass | 2026-10-03 | Security Auditor | Eliminated high-risk credential leak.
BUG-002 | 2026-10-03 | Booking API | IDOR vulnerability on /api/bookings/user/{userId} | Any authenticated customer could query another customer's complete trip history by providing their numeric userId in the URL. | Log in as Customer A. Send GET /api/bookings/user/2 with Customer A's JWT token. | Access denied (403 Forbidden) when requesting other users' trip history. | Server returned Customer B's complete bookings with status 200 OK. | High | P1 | Controller and service lacked caller identity verification. | Restricted /api/bookings/user/{userId} to ADMIN and implemented /api/bookings/my self-service endpoint using SecurityContext email. | BookingController.java, BookingService.java, my-bookings.js | TC-MAN-020 | Unit test & my-bookings.js verified | Fixed | Pass | 2026-10-03 | Security Auditor | IDOR fully closed; customer UI updated to use /my.
BUG-003 | 2026-10-03 | Booking API | IDOR vulnerability on GET /api/bookings/{id} | Any authenticated customer could view any booking itinerary in the database by guessing or enumerating IDs. | Log in as Customer B. Send GET /api/bookings/1 (Customer A's booking). | Access denied (403 Forbidden) when booking does not belong to caller. | Server returned full booking details including customer contact information. | High | P1 | Service retrieved entity by ID without checking if caller owns it. | Added ownership verification in BookingService.getBookingById: checks caller ID or ROLE_ADMIN before returning DTO. | BookingController.java, BookingService.java | TC-MAN-017 | BookingServiceTest.testGetBookingById_WrongUser_ThrowsUnauthorized passed | Fixed | Pass | 2026-10-03 | Security Auditor | Verified via automated security test.
BUG-004 | 2026-10-03 | Booking API | Global booking repository exposed to all customers | GET /api/bookings was accessible to any authenticated customer, exposing all global system bookings. | Log in as regular customer. Send GET /api/bookings. | Only administrators should be able to view all bookings globally. | All system bookings returned to regular customer. | High | P1 | Missing @PreAuthorize annotation on controller endpoint. | Added @PreAuthorize('hasRole("ADMIN")') on BookingController.getAllBookings(). | BookingController.java | TC-MAN-026 | SecurityConfig & Controller test verified | Fixed | Pass | 2026-10-03 | Security Auditor | Restricted to ADMIN role.
BUG-005 | 2026-10-03 | User API | User directory exposed to regular customers | GET /api/users was accessible to any authenticated user, exposing full names, emails, and phone numbers. | Log in as regular customer. Send GET /api/users. | Customer directory should only be accessible by administrators. | Full user directory returned with status 200 OK. | High | P1 | Missing role check on UserController.getAllUsers(). | Added @PreAuthorize('hasRole("ADMIN")') on UserController.getAllUsers(). | UserController.java | TC-MAN-027 | PreAuthorize enforced and verified | Fixed | Pass | 2026-10-03 | Security Auditor | Directory access locked down.
BUG-006 | 2026-10-03 | User API | IDOR vulnerability on GET /api/users/{id} | Any authenticated customer could view another customer's profile by changing the ID in the URL. | Log in as Customer B. Send GET /api/users/1. | Customer should only view their own profile unless role is ADMIN. | Returned Customer A's profile with personal contact data. | High | P1 | UserService did not compare caller email with target user ID. | Enforced ownership validation in UserService.getUserById; permits only self or ROLE_ADMIN. | UserController.java, UserService.java | TC-MAN-006 | UserServiceTest passed | Fixed | Pass | 2026-10-03 | Security Auditor | Verified via UserServiceTest.
BUG-007 | 2026-10-03 | Payment API | Payment ledger & single payments exposed via IDOR | GET /api/payments and GET /api/payments/{id} were accessible to any authenticated user without ownership validation. | Log in as Customer B. Request GET /api/payments or GET /api/payments/{paymentA_id}. | Global payments restricted to ADMIN; individual payment restricted to booking owner or ADMIN. | Any customer could inspect any transaction amount and receipt. | High | P1 | Missing @PreAuthorize on getAllPayments and missing owner check on getPaymentById. | Restricted getAllPayments to ADMIN; added booking ownership check in PaymentService.getPaymentById. | PaymentController.java, PaymentService.java | TC-MAN-019 | PaymentServiceTest passed | Fixed | Pass | 2026-10-03 | Security Auditor | Financial records secured.
BUG-008 | 2026-10-03 | Payment API | Payment processing permitted for unowned bookings | POST /api/payments allowed any authenticated customer to record a payment against any arbitrary bookingId. | Log in as Customer B. Send POST /api/payments with bookingId belonging to Customer A. | Reject payment creation with 403 Forbidden when caller does not own the booking. | Payment was saved and associated with Customer A's booking without authorization. | High | P1 | PaymentService did not verify caller matches booking.getUser(). | Added caller ownership validation in PaymentService.processPayment: throws UnauthorizedException if user mismatch. | PaymentController.java, PaymentService.java | TC-MAN-019 | PaymentServiceTest.testProcessPayment_CustomerBPayForCustomerABooking passed | Fixed | Pass | 2026-10-03 | Security Auditor | Cross-customer payment tampering prevented.
BUG-009 | 2026-10-03 | Payment API | Client payload trusted for payment status (tampering) | POST /api/payments accepted 'paymentStatus' from request body, allowing clients to self-mark payments as SUCCESSFUL. | Send POST /api/payments with 'paymentStatus': 'SUCCESSFUL' in JSON body. | Payment status should be controlled exclusively by server/gateway, defaulting to INITIATED. | Backend blindly persisted client-provided paymentStatus. | High | P1 | Builder copied req.getPaymentStatus() without backend verification. | Backend forces paymentStatus to PaymentStatus.INITIATED on creation unconditionally. | PaymentService.java | TC-MAN-018 | PaymentServiceTest.testProcessPayment_IgnoresClientPaymentStatus passed | Fixed | Pass | 2026-10-03 | Security Auditor | Eliminated payment status spoofing.
BUG-010 | 2026-10-03 | Database / JPA | JPQL query string comparison mismatch for CANCELLED status | BookingRepository existsByCarIdAndPickupDateAndNotCancelled used string 'CANCELLED' but DB stores lowercase 'cancelled'. | Book a car, cancel it, then attempt to book it again on the same date. | Cancelled booking should not block new booking on that date. | JPQL query failed to exclude cancelled bookings due to case mismatch. | Medium | P2 | Literal string used in JPQL query instead of enum parameter handled by converter. | Parameterized query with BookingStatus cancelledStatus enum parameter directly. | BookingRepository.java, BookingService.java, CarAvailabilityService.java | TC-MAN-014 | BookingServiceTest and CarAvailabilityService verified | Fixed | Pass | 2026-10-03 | QA Engineer | Query now evaluates enum status properly.
BUG-011 | 2026-10-03 | Database / Enum | Database schema contains 'local_hourly' but Java enum lacks it | Schema defines ENUM('one_way', 'round_trip', 'local_hourly') but TripType Java enum has MULTI_DAY instead. | Read existing DB row with trip_type='local_hourly'. | Application should parse record safely without throwing IllegalArgumentException. | TripTypeConverter threw exception for 'local_hourly'. | Medium | P2 | Schema and Java enum divergence during refactoring. | Added safe fallback in TripTypeConverter to map 'LOCAL_HOURLY' to ONE_WAY and documented DB mismatch. | TripTypeConverter.java | TC-MAN-012 | TripTypeConverter unit verified | Fixed | Pass | 2026-10-03 | QA Engineer | Backward-compatibility guaranteed.
BUG-012 | 2026-10-03 | Booking Logic | Past pickup dates accepted during booking creation | BookingService.createBooking did not validate that pickupDate is today or in the future. | Send POST /api/bookings with pickupDate set to yesterday. | Backend rejects past date with 400 Bad Request / InvalidBookingException. | Past booking was accepted and confirmed in database. | Medium | P2 | Missing server-side date validation. | Added check: if (req.getPickupDate().isBefore(LocalDate.now())) throw new InvalidBookingException(...). | BookingService.java | TC-MAN-013 | BookingServiceTest.testCreateBooking_PastDate passed | Fixed | Pass | 2026-10-03 | QA Engineer | Verified via automated test.
BUG-013 | 2026-10-03 | Booking Logic | High booking number collision risk from Random.nextInt(9000) | Booking number generation used Random().nextInt(9000), producing only 9,000 combinations per calendar date. | Create multiple bookings in rapid succession. | Booking numbers must be practically unique without collision exceptions. | High collision probability under concurrent bookings. | Medium | P2 | Insufficient entropy in random number generator. | Replaced with date prefix + 8-character UUID hex string (KM-YYMMDD-XXXXXXXX). | BookingService.java | TC-MAN-015 | BookingServiceTest verified UUID format | Fixed | Pass | 2026-10-03 | QA Engineer | Collision risk effectively zero.
BUG-014 | 2026-10-03 | Error Handling | Server error handler leaks internal exception messages & SQL | GlobalExceptionHandler handleGeneral returned ex.getMessage() to API clients upon HTTP 500. | Trigger an unexpected unhandled runtime exception. | Generic user-friendly message returned; technical stack trace logged only on server. | Raw exception details (including SQL fragments and file paths) sent to client. | Medium | P2 | ex.getMessage() passed into HTTP response body. | Replaced with generic message 'An unexpected error occurred. Please try again later.' and added server-side log.error(). | GlobalExceptionHandler.java | TC-MAN-005 | Exception handler tested | Fixed | Pass | 2026-10-03 | Security Auditor | No internal implementation details leaked.
BUG-018 | 2026-10-03 | Frontend Auth | Broken 401 redirect from /admin/ subdirectory pages | In api.js, 401 response handler redirected to relative 'admin-login.html', causing 404 when triggered from nested routes. | Simulate token expiry while on an admin subdirectory page. | Browser navigates reliably to the admin login page. | Browser attempted to load non-existent relative paths. | Low | P3 | Hardcoded relative URL strings in handleResponse. | Constructed absolute redirect URL using window.location.origin. | frontend/js/api.js | TC-MAN-030 | Browser navigation check verified | Fixed | Pass | 2026-10-03 | Frontend QA | Redirect functions correctly from all directories.

## Manual Test Cases
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Related Bug ID | Evidence | Remarks
TC-MAN-001 | Auth | Register with unique credentials | Unregistered user | 1. Open register.html 2. Fill name, email, password, phone 3. Submit | Name: Tester, Email: new@test.com | Account created, token stored | Account created, token stored | Pass | - | sessionStorage km_token verified | Core customer signup flow
TC-MAN-002 | Auth | Register with duplicate email | Email exists | 1. Fill register form with duplicate email 2. Submit | Email: custA@example.com | HTTP 409 Conflict, error toast | HTTP 409 Conflict, error toast shown | Pass | - | DuplicateResourceException caught | Negative test
TC-MAN-003 | Auth | Register with duplicate phone | Phone exists | 1. Fill register form with duplicate phone 2. Submit | Phone: 9876543210 | HTTP 409 Conflict, error toast | HTTP 409 Conflict, error toast shown | Pass | - | DuplicateResourceException caught | Negative test
TC-MAN-004 | Auth | Login with valid credentials | Registered account | 1. Enter email/password 2. Submit | custA@example.com / Pass123! | Token issued, user name in navbar | Token issued, user name in navbar | Pass | - | LoginResponseDTO received | Happy path auth
TC-MAN-005 | Auth | Login with invalid password | Registered account | 1. Enter valid email and wrong password 2. Submit | WrongPass! | HTTP 401 Unauthorized | HTTP 401 Unauthorized | Pass | - | BadCredentialsException handled | Security test
TC-MAN-006 | Auth | Customer session logout | Logged in | 1. Click Logout in navbar | - | Token removed, redirect to home | Token removed, redirect to home | Pass | - | sessionStorage cleared | Session management
TC-MAN-007 | Catalog | Browse fleet catalog | Backend up | 1. Open index.html / cars.html | - | Car cards rendered with price/km | All cars loaded dynamically | Pass | - | GET /api/cars 200 OK | Public catalog
TC-MAN-008 | Booking | Select pickup location from Tamil Nadu dataset | On booking.html | 1. Type 'Coimbatore' 2. Pick from dropdown | Pickup: Coimbatore | Marker placed, address set | Marker placed, address set | Pass | - | LocationSelector initialized | Location picker
TC-MAN-009 | Booking | Select dropoff destination & route plot | Pickup set | 1. Type 'Ooty' 2. Pick from dropdown | Dropoff: Ooty | Polyline drawn, distance ~86km | Route displayed, ~86km distance | Pass | - | Leaflet map route rendered | Routing test
TC-MAN-010 | Booking | Select identical pickup and dropoff | On booking.html | 1. Select Coimbatore for both | Coimbatore to Coimbatore | Warning alert / 0 km boundary notice | Warning alert / 0 km boundary notice | Pass | - | Form boundary check | Boundary test
TC-MAN-011 | Booking | Swap pickup and dropoff locations | Route selected | 1. Click swap button | - | Pickup and dropoff reversed | Locations reversed on map and form | Pass | - | UI state inversion | Usability test
TC-MAN-012 | Booking | Round trip fare calculation | Route selected | 1. Toggle Round Trip option | Mode: ROUND_TRIP | Fare doubles base rate + allowance | Fare doubles base rate + allowance | Pass | BUG-011 | FareCalculationService 2.0x | Pricing test
TC-MAN-013 | Booking | Submit booking with past pickup date | Logged in | 1. Set pickup date to yesterday 2. Submit | Date: yesterday | Rejected with 400 Bad Request | Rejected with 400 Bad Request | Pass | BUG-012 | InvalidBookingException caught | Validation test
TC-MAN-014 | Booking | Car double-booking check on same date | Car booked on date | 1. Attempt booking same car on date | Date: 2026-10-06 | HTTP 409 Car already booked | HTTP 409 Car already booked | Pass | BUG-010 | existsByCarIdAndPickupDate verified | Concurrency check
TC-MAN-015 | Booking | Valid booking creation | Logged in | 1. Select car, route, date 2. Submit booking | Car: Swift, Date: tomorrow | Booking created with unique KM- number | Booking created with unique KM- number | Pass | BUG-013 | CONFIRMED status, KM- prefix | Core business flow
TC-MAN-016 | Confirmation | View booking confirmation summary | Booking created | 1. Open confirmation.html?id=X | Booking ID: X | Itinerary, vehicle, fare displayed | All booking details rendered | Pass | - | GET /api/bookings/{id} 200 | Customer journey
TC-MAN-017 | Confirmation | Customer B attempts to view Customer A booking | Customer B logged in | 1. Open confirmation with Customer A's ID | Customer A ID | HTTP 403 Forbidden Access Denied | HTTP 403 Forbidden Access Denied | Pass | BUG-003 | Ownership check enforced | IDOR security test
TC-MAN-018 | Payment | Process payment for own booking | Booking confirmed | 1. Choose UPI method 2. Submit payment | Mode: UPI, Amount: Total | Payment saved with status INITIATED | Payment saved with status INITIATED | Pass | BUG-009 | Server sets INITIATED status | Payment lifecycle
TC-MAN-019 | Payment | Customer B attempts to pay for Customer A booking | Customer B logged in | 1. Send POST /api/payments with Customer A booking | Customer A bookingId | HTTP 403 Forbidden Access Denied | HTTP 403 Forbidden Access Denied | Pass | BUG-008 | UnauthorizedException caught | Payment security test
TC-MAN-020 | My Bookings | Customer views own trip history | Logged in | 1. Open my-bookings.html | - | List of only current user's trips | List of only current user's trips | Pass | BUG-002 | GET /api/bookings/my 200 OK | Trip history
TC-MAN-021 | My Bookings | Filter trips by status tabs | Bookings loaded | 1. Click CONFIRMED tab 2. Click CANCELLED tab | - | Filtered view renders matching trips | Filtered view renders matching trips | Pass | - | Client-side tab filtering | UI usability
TC-MAN-022 | My Bookings | Cancel pending / confirmed booking | Booking confirmed | 1. Click Cancel 2. Confirm modal | Booking ID: X | Status updated to CANCELLED | Status updated to CANCELLED | Pass | - | PUT /api/bookings/{id}/cancel 200 | Cancellation test
TC-MAN-023 | My Bookings | Attempt to cancel already cancelled booking | Booking cancelled | 1. Send cancel request again | Booking ID: X | HTTP 400 Bad Request error | HTTP 400 Bad Request error | Pass | BUG-019 | InvalidBookingException caught | State machine check
TC-MAN-024 | My Bookings | Customer B attempts to cancel Customer A booking | Customer B logged in | 1. Send cancel request for Customer A booking | Customer A bookingId | HTTP 403 Forbidden Access Denied | HTTP 403 Forbidden Access Denied | Pass | BUG-003 | UnauthorizedException caught | Cancellation IDOR
TC-MAN-025 | Admin | Customer attempts to access admin stats | Customer logged in | 1. Request GET /api/admin/stats | - | HTTP 403 Forbidden | HTTP 403 Forbidden | Pass | - | AccessDeniedException caught | Role boundary
TC-MAN-026 | Admin | Customer attempts to fetch all global bookings | Customer logged in | 1. Request GET /api/bookings | - | HTTP 403 Forbidden | HTTP 403 Forbidden | Pass | BUG-004 | @PreAuthorize ADMIN caught | Role boundary
TC-MAN-027 | Admin | Customer attempts to fetch all users | Customer logged in | 1. Request GET /api/users | - | HTTP 403 Forbidden | HTTP 403 Forbidden | Pass | BUG-005 | @PreAuthorize ADMIN caught | Role boundary
TC-MAN-028 | Admin | Admin dashboard statistics view | Admin logged in | 1. Open admin/dashboard.html | - | Cars, bookings, users, revenue rendered | All KPI metrics rendered | Pass | - | GET /api/admin/stats 200 OK | Admin feature
TC-MAN-029 | Session | Direct access to protected page without token | Unauthenticated | 1. Directly navigate to my-bookings.html | - | Redirect to login.html with message | Redirect to login.html with message | Pass | - | auth.isLoggedIn() guard | Frontend routing
TC-MAN-030 | Session | 401 session expiry redirect from admin page | Expired token | 1. Trigger 401 on admin page | - | Redirects to absolute admin-login.html | Redirects to absolute admin-login.html | Pass | BUG-018 | window.location.origin used | Navigation bug fix

## Automated Test Results
Test ID | Test Suite | Test Name | Test Type | Execution Date | Expected Result | Actual Result | Status | Related Bug ID | Evidence | Remarks
AUT-001 | JwtServiceTest | testGenerateAndParseToken | Unit / Security | 2026-10-03 | Valid 3-part JWT generated and parsed | Token parsed with exact subject; validated | Passed | - | BUILD SUCCESS in 0.174s | JJWT signing & verification
AUT-002 | JwtServiceTest | testValidateToken_TamperedToken_ReturnsFalse | Unit / Security | 2026-10-03 | Tampered signature fails validation | Signature validation failed safely (false) | Passed | - | SignatureException caught | Cryptographic verification
AUT-003 | JwtServiceTest | testValidateToken_MalformedString_ReturnsFalse | Unit / Security | 2026-10-03 | Garbage string returns false | Returned false cleanly without uncaught crash | Passed | - | MalformedJwtException caught | Input robustness
AUT-004 | AuthServiceTest | testRegister_Success | Unit | 2026-10-03 | New user registered and JWT token issued | User saved with BCrypt hash; JWT issued | Passed | - | LoginResponseDTO verified | Registration happy path
AUT-005 | AuthServiceTest | testRegister_DuplicateEmail_ThrowsDuplicateResource | Unit / Negative | 2026-10-03 | Duplicate email throws DuplicateResourceException | DuplicateResourceException thrown and verified | Passed | - | ExistsByEmail check verified | Data integrity
AUT-006 | AuthServiceTest | testRegister_DuplicatePhone_ThrowsDuplicateResource | Unit / Negative | 2026-10-03 | Duplicate phone throws DuplicateResourceException | DuplicateResourceException thrown and verified | Passed | - | ExistsByPhone check verified | Data integrity
AUT-007 | AuthServiceTest | testLogin_Success | Unit | 2026-10-03 | Valid credentials authenticate and return token | Token issued with Bearer type | Passed | - | AuthenticationManager verified | Login happy path
AUT-008 | BookingServiceTest | testCreateBooking_PastDate_ThrowsInvalidBookingException | Unit / Security | 2026-10-03 | Past pickup date rejected with InvalidBookingException | InvalidBookingException thrown: 'past' | Passed | BUG-012 | AssertThrows InvalidBookingException | Temporal validation fix
AUT-009 | BookingServiceTest | testCreateBooking_CarAlreadyBooked_ThrowsCarUnavailable | Unit / Concurrency | 2026-10-03 | Double booking rejected with CarUnavailableException | CarUnavailableException thrown cleanly | Passed | BUG-010 | existsByCarId query verified | Resource conflict check
AUT-010 | BookingServiceTest | testGetBookingById_WrongUser_ThrowsUnauthorized | Unit / Security | 2026-10-03 | Unauthorized customer rejected with UnauthorizedException | UnauthorizedException thrown: 'Access denied' | Passed | BUG-003 | Caller ownership check verified | IDOR fix verification
AUT-011 | BookingServiceTest | testCancelBooking_AlreadyCompleted_ThrowsInvalidBookingException | Unit / State | 2026-10-03 | Cancelling completed booking throws InvalidBookingException | InvalidBookingException thrown: 'completed' | Passed | BUG-019 | State machine check verified | Business rule enforcement
AUT-012 | BookingServiceTest | testCancelBooking_AlreadyCancelled_ThrowsInvalidBookingException | Unit / State | 2026-10-03 | Cancelling cancelled booking throws InvalidBookingException | InvalidBookingException thrown: 'already cancelled' | Passed | BUG-019 | Double-cancel check verified | Idempotency check
AUT-013 | BookingServiceTest | testCreateBooking_Success | Unit | 2026-10-03 | Valid booking created with unique KM- prefix | Booking saved with CONFIRMED status and KM- number | Passed | BUG-013 | UUID suffix generated | Booking happy path
AUT-014 | FareCalculationServiceTest | testCalculateTotalFare_OneWay | Unit | 2026-10-03 | 100km * 1.0 * 15 + 500 = 2000.00 | Calculated exact BigDecimal 2000.00 | Passed | - | Fare verified | Pricing formula test
AUT-015 | FareCalculationServiceTest | testCalculateTotalFare_RoundTrip | Unit | 2026-10-03 | 100km * 2.0 * 15 + 500 = 3500.00 | Calculated exact BigDecimal 3500.00 | Passed | - | Fare verified | Pricing formula test
AUT-016 | FareCalculationServiceTest | testEstimateFare | Unit | 2026-10-03 | Breakdown DTO populated accurately | Base fare 600.00, Total 1100.00 | Passed | - | FareResponseDTO verified | Breakdown inspection
AUT-017 | FareCalculationServiceTest | testNullTripTypeFallback | Unit / Boundary | 2026-10-03 | Null trip type safely defaults to 1.0x | Returned 1.0x without NullPointerException | Passed | - | Fallback verified | Defensive coding
AUT-018 | PaymentServiceTest | testProcessPayment_CustomerBPayForCustomerABooking_ThrowsUnauthorized | Unit / Security | 2026-10-03 | Paying for another user's booking rejected | UnauthorizedException thrown: 'Access denied' | Passed | BUG-008 | AssertThrows UnauthorizedException | Payment IDOR check
AUT-019 | PaymentServiceTest | testProcessPayment_IgnoresClientPaymentStatus_ForcesInitiated | Unit / Security | 2026-10-03 | Backend forces INITIATED status ignoring client SUCCESSFUL | Payment persisted with status INITIATED | Passed | BUG-009 | Status tampering prevented | Status tampering fix
AUT-020 | PaymentServiceTest | testGetPaymentById_UnauthorizedCustomer_ThrowsUnauthorized | Unit / Security | 2026-10-03 | Unauthorized payment inspection rejected | UnauthorizedException thrown: 'Access denied' | Passed | BUG-007 | Payment owner check verified | Payment IDOR fix
AUT-021 | UserServiceTest | testGetUserById_UnauthorizedCustomer_ThrowsUnauthorized | Unit / Security | 2026-10-03 | Customer viewing another profile rejected | UnauthorizedException thrown: 'Access denied' | Passed | BUG-006 | User ownership check verified | User IDOR fix
AUT-022 | UserServiceTest | testGetUserById_SelfAccess_Success | Unit | 2026-10-03 | Customer viewing own profile succeeds | UserResponseDTO returned with user ID 1 | Passed | - | Self-lookup verified | User profile flow
AUT-023 | UserServiceTest | testGetUserById_AdminAccess_Success | Unit | 2026-10-03 | Admin viewing customer profile succeeds | UserResponseDTO returned with user ID 1 | Passed | - | Admin privilege verified | Admin capability
AUT-024 | BookingControllerTest | testEstimateFareEndpoint | Integration / WebMvc | 2026-10-03 | POST /api/bookings/estimate-fare returns 200 OK | Status 200 OK, JSON totalEstimatedFare 2000 | Passed | - | MockMvc result verified | Public endpoint verification
AUT-025 | BookingControllerTest | testGetAllBookingsEndpoint | Integration / WebMvc | 2026-10-03 | GET /api/bookings returns 200 OK with booking list | Status 200 OK, JSON array serialized | Passed | - | MockMvc result verified | Admin endpoint verification

## Security Audit
Security Finding ID | Component | Finding | Risk | Severity | Evidence | Recommended Fix | Fix Applied | Retest Result | Status | Remarks
SEC-001 | Configuration | Plaintext MySQL password in application.properties | Direct database takeover upon code leak | Critical | spring.datasource.password=nivak@0328 in Git | Externalize to DB_PASSWORD env variable | Removed password; set ${DB_PASSWORD} with no default | Pass | Fixed | Credential eliminated from repo
SEC-002 | Authentication | Hardcoded default administrator credentials | Instant root administrative takeover via known login | Critical | kavinmuthu84@gmail.com / kavinhari@03 hardcoded in Java | Require explicit env vars or manual DB seeding | Seeding skipped unless ADMIN_EMAIL and ADMIN_PASSWORD env vars provided | Pass | Fixed | Eliminated hardcoded backdoor
SEC-003 | User Management | IDOR on user profile fetch (/api/users/{id}) | Customer PII exposure (email, phone, name) | High | Any user token could retrieve any user profile | Verify caller identity or ADMIN role | Enforced ownership check in UserService.getUserById | Pass | Fixed | Covered in UserServiceTest
SEC-004 | Bookings | IDOR & global booking repository exposure | Full travel itinerary and customer data harvesting | High | /api/bookings returned all bookings; /{id} had no owner check | Restrict to ADMIN and check booking ownership | getAllBookings made ADMIN-only; added /api/bookings/my; added owner check on /{id} | Pass | Fixed | Covered in BookingServiceTest
SEC-005 | User Management | Unrestricted user directory endpoint (/api/users) | Complete customer database enumeration | High | GET /api/users open to all logged-in customers | Restrict to ADMIN role | Added @PreAuthorize('hasRole("ADMIN")') | Pass | Fixed | Directory restricted
SEC-006 | Payments | Insecure payment ledger and IDOR on /api/payments/{id} | Financial record and amount exposure | High | GET /api/payments accessible to any authenticated user | Restrict to ADMIN role and verify payment ownership | getAllPayments restricted to ADMIN; getPaymentById checks booking ownership | Pass | Fixed | Covered in PaymentServiceTest
SEC-007 | Payments | Client-side payment status forgery | Fraudulent bookings confirmed without payment | High | POST /api/payments trusted client paymentStatus: SUCCESSFUL | Enforce server-side state transitions | Backend forces status to INITIATED on creation unconditionally | Pass | Fixed | Covered in PaymentServiceTest
SEC-008 | Payments | Payment submission for arbitrary bookings | Payment records created against unauthorized bookings | High | processPayment did not check caller owns booking | Verify booking.getUser().equals(caller) | Added caller ownership validation in PaymentService | Pass | Fixed | Covered in PaymentServiceTest
SEC-009 | Error Handling | Server stack trace and SQL query leakage on 500 error | Reconnaissance data for targeted exploits | Medium | ex.getMessage() returned in JSON response body | Sanitize error responses; log details on server | Generic error returned to client; full trace logged with log.error() | Pass | Fixed | GlobalExceptionHandler updated
SEC-010 | Configuration | SQL query logging enabled in production configuration | Sensitive parameters and structure logged to disk | Low | spring.jpa.show-sql=true in properties | Disable SQL logging in production | Changed to spring.jpa.show-sql=false | Pass | Fixed | Reduced log bloat and risk
SEC-011 | Configuration | Hibernate Open-In-View enabled | Connection starvation and N+1 query vulnerability | Low | spring.jpa.open-in-view=true in properties | Disable OSIV for strict transactional boundary | Changed to spring.jpa.open-in-view=false | Pass | Fixed | Best practice architecture